## Sheet1
Month | Academic Week | Date | Tasks | Status | Comment
SEMESTER 1
Sept | 1 | 2014-09-15 | Research ideas and sensors | x
|  |  | Talk to Susan | x
|  |  | Decide idea | x
|  |  | Email Damon Berry | x
| 2 | 2014-09-22 | Research existing technology | x
|  |  | Meeting with Mark Deegan | x
|  |  | Write interview questions | x
|  |  | Write transcript | x | Written from notes + memory
|  |  | Interview with Mr. Edward Moloney | x
| 3 | 2014-09-29 | Meeting with Damon Berry | x
|  |  | Send questionnaire to Irish Sleep Apnoea Trust | x
|  |  | Submit project proposal | x
|  |  | Download Andriod SDK + ADT Plugin | x
|  |  | Make table of sensors (functions, pros, cons, price, availability, etc.) | x
|  |  | Damian Gordon to sign proposal | x
October | 4 | 2014-10-06 | Finalise concept
|  |  | plan weekly tasks | o | Not complete
|  |  | Order sensors |  | *URGENT*
|  |  | Begin thesis/interim report (background + concept) | x
|  |  | Draw system architecture and decide technologies needed | x
|  |  | Write CSV file opening class | x
|  |  | Revise andriod development | x
|  |  | Research required referencing for interim report/thesis | x
|  |  | Read 2 academic papers/articles/journals/books | x
| 5 | 2014-10-13 | Research (+ ask Damon Berry) emulation of synchronous bluetooth transmission
Research coding bluetooth connection
|  |  | Print proposal | x
First supervision meeting + tasks from meeting
Send questionnaire to another sleep specialist (Dr. Richard Costello ?)
Thesis/interim report writing (2 pages - research + architectural design draft)
Research which values (or combination) indicate an occurance of an apnoea
research existing formulas for detecting apnoeas
| 6 | 2014-10-20 | Make survey for sleep apnoea sufferers (+ ask Cathy for contact's email)
Thesis/interim report writing (review of existing (competitor) apps and technology)
| 7 | 2014-10-27 | Thesis writing(review of existing(competitor) apps and technology (+issues with them) and innovations with my project)
Interim report writing (overview of project + technologies used)
November | 8 | 2014-11-03 | Thesis/interim report writing (drawbacks of concept + software methodologies)
| 9 | 2014-11-10 | Interim report writing (plans until project deadline)
| 10 | 2014-11-17 | Interim report writing (progress to date)
| 11 | 2014-11-24 | Interim report writing (issues encountered so far)
December | 12 | 2014-12-01 | Interim report writing (remaining sections to complete)
| 13 | 2014-12-08 | Interim report writing (final draft)
| 14 - Exams | 2014-12-15 | Submission of interim report
| Xmas | 2014-12-22 | Thesis writing (review of technologies used (and not used))
| Xmas | 2014-12-29 | Thesis writing (review of technologies used (market evaulation + survey data))
SEMESTER 2
January | 15 - Exams | 2015-01-05 | Thesis writing (data input - bluetooth API, methods, data types)
|  | 2015-01-12 | Thesis writing (data storage)
| 1 | 2015-01-19 | Reassess workload and approach based on critique from interim report
Thesis writing (web functionality + data upload)
| 2 | 2015-01-26 | Thesis writing (algorithm design)
February | 3 | 2015-02-02 | Thesis writing (algorithm design)
| 4 | 2015-02-09 | Thesis writing (GUI prototype/screenshots)
| 5 | 2015-02-16 | Thesis writing (GUI design)
| 6 | 2015-02-23 | Thesis writing (final functionality)
March | 7 | 2015-03-02 | Thesis writing (Testing - software and user)
| 8 | 2015-03-09 | Thesis writing (issues encountered, bugs, changes made)
| 9 | 2015-03-16 | Thesis writing (review of chosen approach and technology/concept - what would I do differently?)
| 10 | 2015-03-23 | Thesis writing (conclusion + references)
| Easter | 2015-03-30 | Thesis (Proof reading + obtain impartial/expert opinion)
April | Easter | 2015-04-06 | Thesis (final draft)
| 11 | 2015-04-13
| 12 | 2015-04-20
| 13 | 2015-04-27
May | 14 | 2015-05-04
| 15 - Exams | 2015-05-11